## 🗺 Master Plan
INKDOWN / NOTESHELL — PHASE 2 MASTERPLAN ¦ Mar 17 → Apr 30, 2026
# | Initiative | Description | Pillar | Owner | Start | End | Status
1 | Agent Quality Audit | Stress-test all 7 agents (editor, deep, note, chat, secretary, research, course). Fix streaming bugs, harden error handling, write regression tests. | 🚀 Launch | QQ + Claude Code | Mar 17 | Mar 28 | 🟡 In Progress
2 | Billing System Design | Design Supabase schema: subscriptions, usage, credits tables. Scaffold Stripe integration in Hono API. Free-credit logic for first-time users. | 🚀 Launch | QQ + Claude Code | Mar 24 | Apr 4 | ⚪ Planned
3 | Free Credits Onboarding Flow | Define credit tiers. Build UI for credit counter, upgrade CTA, low-balance warning. Newcomer bonus logic. | 🚀 Launch | QQ | Apr 1 | Apr 11 | ⚪ Planned
4 | MCP Server for Distribution | Package Inkdown's note/secretary/research features as MCP tools. Publish to Claude Code / Codex ecosystem for discovery. | 🚀 Launch | QQ + Claude Code | Apr 7 | Apr 18 | ⚪ Planned
5 | In-App Feedback System | Build feedback widget inside platform → Supabase table → Slack notification. Add NPS prompt after key actions. | 📣 Marketing | QQ + Claude Code | Mar 24 | Mar 31 | ⚪ Planned
6 | Company Gmail + Forms Setup | Set up company Gmail (e.g. hello@inkdown.app). Create Google Forms for structured feedback, interview requests, waitlist sign-up. | 📣 Marketing | QQ | Mar 17 | Mar 21 | 🟡 In Progress
7 | Designer Recruitment | Find & brief a designer for: social post templates, banner graphics, demo video storyboard. Provide brand brief. | 📣 Marketing | QQ | Mar 17 | Mar 24 | 🟡 In Progress
8 | Demo Video Production | Script, record, and edit a 60–90s product demo video. Showcase note-taking, AI secretary, and brain dump flow. | 📣 Marketing | QQ + Designer | Mar 28 | Apr 11 | ⚪ Planned
9 | Launch Campaign — Social | Facebook + Instagram campaign. Schedule posts, run scrappy 'high school project' tone content. Hashtags, reels, stories. | 📣 Marketing | QQ + Designer | Apr 7 | Apr 30 | ⚪ Planned
10 | User Interview Campaign | Target 20+ interviews: students, recruiters, professors. Use Google Forms + DM outreach. Synthesize feedback weekly. | 📣 Marketing | QQ | Mar 24 | Apr 30 | ⚪ Planned
11 | Proposed Board UI Pattern | Design + build a reusable 'AI proposal → user review → commit' UI component. Used across brain dump, secretary, and agent edits. | 🤖 Autonomous AI | QQ + Claude Code | Mar 31 | Apr 14 | ⚪ Planned
12 | iPhone Brain Dump Integration | Build API endpoint to receive plain-text dumps. Triage agent parses intent: #note tags, meeting references, task references. Returns proposed board JSON. | 🤖 Autonomous AI | QQ + Claude Code | Apr 7 | Apr 25 | ⚪ Planned
13 | Intent Triage Agent | New AI agent: takes raw text → classifies as note/meeting/task/free-form. Outputs structured intents for proposed board. Handles hashtag syntax (#note: title). | 🤖 Autonomous AI | QQ + Claude Code | Apr 7 | Apr 21 | ⚪ Planned
14 | AI Architecture Redesign | Rethink agent orchestration for autonomy + reliability. Cross-feature connectivity: notes ↔ calendar ↔ tasks ↔ research. Event-driven sync layer. | 🤖 Autonomous AI | QQ + Claude Code | Apr 14 | Apr 30 | ⚪ Planned
15 | Soft Launch 🎉 | Public announcement. Free credits active. Feedback system live. Social campaign running. First 50 users onboarded. | 🚀 Launch | QQ | Apr 28 | Apr 30 | ⚪ Planned
PILLARS: 🚀 Launch (Product) 📣 Marketing & Community 🤖 Autonomous AI & iPhone Sync

## 📅 Gantt
INKDOWN — PHASE 2 GANTT ¦ Mar 17 → Apr 30, 2026
|  |  | MARCH 2026 | [10 empty] | APRIL 2026
# | Initiative | Pillar | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T
|  |  | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30
1 | Agent Quality Audit | 🚀 Launch
2 | Company Gmail + Forms | 📣 Marketing | bar: 17 to 20
3 | Designer Recruitment | 📣 Marketing
4 | Billing System Design | 🚀 Launch | bar: 24 to 3
5 | In-App Feedback System | 📣 Marketing
6 | User Interview Campaign | 📣 Marketing | bar: 24 to 30
7 | Free Credits Flow | 🚀 Launch
8 | Proposed Board UI | 🤖 Auto AI | bar: 31 to 14
9 | Demo Video Production | 📣 Marketing
10 | MCP Server Distribution | 🚀 Launch | bar: 7 to 17
11 | Intent Triage Agent | 🤖 Auto AI
12 | iPhone Brain Dump API | 🤖 Auto AI | bar: 7 to 24
13 | Social Campaign Launch | 📣 Marketing
14 | AI Architecture Redesign | 🤖 Auto AI | bar: 14 to 30
15 | 🎉 SOFT LAUNCH | 🚀 Launch
LEGEND: |  |  | 17: P1 Launch; 23: P2 Marketing; 27: P3 Auto AI; 2: 🎉 Launch Day

## 🏃 Sprint Breakdown
INKDOWN — SPRINT BREAKDOWN ¦ 6-Week Execution Plan
Week | Theme / Goal | Key Tasks | Pillar | Success Metric
W1 Mar 17–21 | Foundation & Quick Wins | • Agent audit begins (editor + deep agent) • Company Gmail + forms setup • Designer brief prepared • Agent regression tests for editor agent | 🚀 + 📣 | Gmail live, 1 agent hardened, designer briefed
W2 Mar 24–28 | AI Quality + Feedback Loop | • Secretary + note agent audit • Billing schema designed (Supabase) • In-app feedback widget shipped • Demo video scripting begins | 🚀 + 📣 | Feedback system live, billing schema merged
W3 Mar 31 – Apr 4 | Proposed Board + Billing Dev | • Proposed Board UI component built • Stripe integration scaffolded • Demo video recorded • User interview outreach starts (target 10+) | 🚀 + 🤖 | Proposed Board component in codebase, Stripe keys wired
W4 Apr 7–11 | iPhone Integration + Launch Prep | • Brain dump API endpoint • Intent Triage Agent v1 • Free credits flow + onboarding UI • MCP server v1 published • Demo video edited + reviewed | 🚀 + 🤖 | Brain dump endpoint live, 15+ user interviews done
W5 Apr 14–18 | Autonomous AI + Campaign Fires Up | • AI Architecture redesign (phase 1) • iPhone sync proposed board integration • Social media campaign begins (Instagram, Facebook) • MCP distribution polish | 🤖 + 📣 | Social campaign launched, architecture doc updated
W6 Apr 21–30 | Launch Week 🎉 | • Full system QA pass • Free credits active for all new users • Public announcement on social • Soft launch Apr 28 • Collect feedback + triage immediately | 🚀 + 📣 | 50 users onboarded, feedback flowing in

## 📊 Success Metrics
INKDOWN — SUCCESS METRICS BY PILLAR
Metric | Target by Apr 30 | Current | % Progress | Notes
Agents hardened (of 7) | 7 agents | 0 | – | All agents pass regression + stress tests
Billing system live | Yes | No | – | Stripe integration, Supabase schema
Free credits active | Yes | No | – | Newcomer bonus flow complete
MCP server published | v1 live | – | – | Inkdown tools on Claude Code ecosystem
User interviews completed | 20+ interviews | 0 | – | Students, recruiters, professors
Feedback widget live | Yes | No | – | In-app widget → Supabase → Slack
Company Gmail set up | Yes | No | – | hello@inkdown.app or similar
Social posts published | 10+ posts | 0 | – | Facebook + Instagram, campaign running
Demo video live | Yes | No | – | 60–90s, all 3 pillars shown
Proposed Board UI live | Yes | No | – | Reusable component, used in 2+ flows
Brain dump API endpoint | Yes | No | – | Receives text, returns proposed board JSON
Intent Triage Agent v1 | Yes | No | – | #note / meeting / task parsing
New users onboarded | 50+ users | 0 | – | Via soft launch Apr 28
NPS score (first cohort) | ≥ 7.0 | – | – | Collected via in-app feedback